## HotelHub Project Timelines
HotelHub | HotelHub Project Timelines
| Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May
| Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4
Analysis and Planning | bar: Feb Week1 to Feb Week2
Requirement Gathering | bar: Feb Week2 to Feb Week3
Design and Prototyping | bar: Feb Week4 to Mar Week2
Software Development | bar: Mar Week3 to Apr Week2
QA Testing | bar: Apr Week3 to Apr Week4
UAT Testing | bar: May Week1 to May Week2
Deployment | bar: May Week3
Maintainance and Updates | bar: May Week3 to May Week4